## Cover Sheet
CTS Nordics
PROJECT DCM103
Application for Payment
Bulk Data Centers N01 DCM103 A5
Application for Payment No.01 - Feb 26

## Executive Summary
PROJECT DCM103 | [5 empty] | CTS Nordics
Application for Payment No.01 - Feb 26
EXECUTIVE SUMMARY
Work Breakdown Structure | Value | % Progress To Date | Cumulative to Date | Previously Certified | In the Period |  | Comments
BUILDING ELEMENTS | 311868817 | 14 % | 37658878 |  | 37658878
Substructure Building 1A
Superstructure Building 1A |  |  | 37658878 |  | 37658878
Superstructure Office Building
Passenger and Goods Lifts
Fitout to Technical Spaces | 15588000
MECHANICAL INSTALLATIONS | 186147266
Mechanical Installations | 167670000
Heating | 474044
Sanitary Installations | 4779434
Fire Fighting
Heat Pump & Refrigeration
Moist Treatment
Water Treatment | 476634 | 0%
Process Mechanical Systems | 12747154
ELECTRICAL INSTALLATIONS
Electrical Installation | 231397848 | 3 % | 3533298 |  | 3533298
Electric Basic Installations
UPS System | 20949000
Emergency lighting | 10001700
Lightning | 18100000
Lighting | [6 empty] | 1 335 096 estimated
Supply of Power | 20000000
Emergency Electric Power
Telecom/Data
SPECIAL PACKAGES | 98506800
DTA Basic Installations
Integrated/Communications
Process Systems
BMS/Automation
Automation | 68481756
FITOUT DATA HALLS (2 x 18 MW)
Fitout - WA ALL 1 (Colocation)
Fitout - WA ALL 1 (Final Fitout)
POOL, GENERATORS & CHILLERS
POOL - 2 x EMW (Exclusive Of Transport) | 474489222 | 14 % | 82987968 | 0 | 82987968
POOL - 2 EMW Transportation
Residual 630kVA Electrical (Mgmt only based on PC) yet to be received from BVA
Diesel for generators | 73632000
Chillers (10 Chillers) | 7450000 |  |  |  | 9432778
Commissioning (Mechanical and Electrical) | 68484476 | 0 %
EXTERNAL WORKS AND LANDSCAPING
External Works and Landscaping | 34860000
Preliminaries
Preliminaries Incl. CM, Mechanical and Electrical |  | 24 % | 54228446
PROJECT TOTAL (Exclusive of VAT & CONTINGENCIES) | N 1 848 422 821 | 12 % | 399794321 |  | 399794321
Change Account | 30800224
Change Account | 80807274
PROJECT TOTAL + Change Account (Exclusive of VAT & COMMISSIONING) | N 1 834 102 807 | 12 % | 399794321 |  | 399794321
Downpayment / Payback
|  | Downpayment Payback - XXX | 30000000 | 27b Invoice 003
Downpayment Payback - XXX
|  | Downpayment Payback - XXX | 87537545 | 27b Invoice 0005
|  | Downpayment Payback - XXX | 141649440 | 27b Invoice 0006
Downpayment Payback - XXX
Downpayment Payback - XXX
Downpayment Payback - XXX
Downpayment Payback - XXX
|  | TOTAL GROSS Valuation | 568991653.31
|  | Deduct 5% Retention | 1611638.84
|  | Net Take Valuation | 569955718.65
|  | Deduct Previous Valuation | 487127165 | Based on what has been paid to the paid to date
|  | Net Valuation in period | 882834555.83

## Breakdown
PRELIMINARIES
CTS Nordics
Location ID |  |  | Element ID | Compo | Compo | Compet Type | Description | Quantity | Unit | Unit Cost (NOK) | Total Cost (NOK) | Project CMT | GMP Value | Fee | GMP Value incl. Fee
B | S | E |  | s | ID (-) | Type
PRELIMINARIES
A | PR | [5 empty] | PRELIMINARIES |  |  |  | 290436583 |  | 8241693
|  |  | 1.1 |  |  |  | CTS Management | 56 | Mts | 30600 | 8241693
|  |  |  | CTS | 1.1.1 |  | Project Director | 50 | % | 81600 | 4080000
|  |  |  | CTS | 1.1.1 |  | Project Manager CM | 100 | % | 102000 | 0
|  |  |  | CTS | 1.1.3 |  | Design Manager |  |  |  | 0
|  |  |  | CTS | 1.1.4 |  | Site Manager For CM |  |  |  | 0
|  |  |  | CTS | 1.1.5 |  | QS Manager |  |  |  | 0
|  |  |  | CTS | 1.1.6 |  | Planner |  |  |  | 0
|  |  |  | CTS | 1.1.7 |  | Cost Manager |  |  |  | 0
|  |  |  | CTS | 1.1.8 |  | Site Manager Controls & Specs Manager |  |  |  | 0
|  |  |  | CTS |  |  | QA/QC Manager |  |  |  | 0
|  |  |  | CTS |  |  | Assistant Site Manager |  |  |  | 0
|  |  |  | CTS |  |  | Logistics Manager |  |  |  | 0
|  |  |  | CTS |  |  | Admin/Document Controller |  |  |  | 0
|  |  |  | CTS |  |  | BIM Manager/BIM Coordinator |  |  |  | 0
|  |  |  | CTS |  |  | Document Controller/Asst.Admin |  |  |  | 0
|  |  |  | CTS |  |  | Procurement Manager |  |  |  | 0
|  |  |  | CTS |  |  | HSE Manager |  |  |  | 0
|  |  |  | CTS |  |  | HSE Officer |  |  |  | 0
|  |  |  | CTS |  |  | Site Engineer |  |  |  | 0
|  |  |  | CTS |  |  | Commissioning Manager |  |  |  | 0
|  |  | 1.2 |  |  |  | Site Facilities
DC Office
DC Canteen
DC Toilet
PR office set-up/demob
HSE equipment
Storage
Camp Manager
Camp running costs
Cleaning (office/canteen)
|  |  | 1.3 |  |  |  | Site Security
Site security (24 hour shifts)
|  |  | 1.4 |  |  |  | Site Clearance
Pre-development clearance
In-depth cleaning of the WS for MPE
|  |  | 1.5 |  |  |  | Site Infrastructure
Temporary road, internal and Maintenance Roads, utility infra
Welfare/Canteen (mobile)
Barracks apartment complex
Site perimeter fencing and gates, prod. active x
|  |  | 1.6 |  |  |  | Site Signage - Visitors Reception
Site Fencing - Visitors Reception
Site signage
|  |  | 1.7 |  |  |  | Waste Management
Construction Waste Management by Conv.
|  |  | 1.8 |  |  |  | Master Media
Drone allowance
Media allowance
|  |  | 1.9 |  |  |  | Remote Compliance
Mobile/web air monitoring system
Dust monitoring
|  |  | 1.10 |  |  |  | Temporary Services during construction
|  |  | 1.11 |  |  |  | Site Signalisation
|  |  | 1.12 |  |  |  | Site IT/Network System/Video Install
IT equipment (PC, screens, printer etc)
Server and telecom installation/ICT/decommission
Temporary Power Supply
CTS Staff housing/Apartments
|  |  | 1.13 |  |  |  | Surveys
Topography
|  |  | 1.14 |  |  |  | Construction plant / Mobile Equipment
Tower crane(s) / Mobile crane
Forklift
Scissor lift / cherry picker, other
|  |  | 1.15 |  |  |  | Consultant Fees
Construction charges (Water)
Construction charges (Electricity)
Construction charges Internal
|  |  | 1.15 |  |  |  | Project Insurances
ENABLING WORKS AND SUBSTRUCTURE
[7 empty] | ENABLING WORKS AND SUBSTRUCTURE |  |  |  | 14360565 |  | 4800000
|  |  | 2.1 |  |  |  | GROUND FLOOR 1A
Earthworks
DV | GSN |  |  |  | 11.010 |  | Cutting and grubbing / Site strip
ENABLING WORKS
Enabling Works
Temporary works (as per build)
|  |  | 2.2 |  |  |  | Construction Pit
Underground utilities / new route (i.e. HV offload line)
Underpinning to adj buildings if required to prevent wall collapses
Piling works
Construction/excavation works for cellars, in-ground sumps/SOG
Dynamic Provisional
Foundations, slab on Elution, inc concrete and reinforcement. Inclusive of the
formwork but exclusive of the specialist sprayed concrete subcontractor
Oil separator(s) grading under transition MG 55 RAPS C1 + MEPC1
Enabling and Earthworks Total: 0
SUPERSTRUCTURE 1A
[7 empty] | SUPERSTRUCTURE 1A |  |  |  | 311868817
STRUCTURAL FRAME
|  |  | 22A |  |  |  | Structural Frame
[7 empty] | Structural Steel: ground to first floor (including full beam) |  | Item
Structural Steel: 1st & 2nd floor incl. purlins & steelwork
Additional allowance of 2.5% for secondary support steel
|  |  | 22A |  |  |  | Fire Protection to Load Bearing Structures
Intumescent paint for structural steel
|  |  | 22A |  |  |  | Columns
Columns
|  |  | 22A |  |  |  | Bracing Structures
Bracing structures - as engineered to double leaf doors
Non Load Bearing Internal Walls
Roof Load Bearing Walls
INTERNAL WALLS
|  |  | 25A |  |  |  | Top Skin, Floor Slabs, Slab on Ground
Reinforced concrete floor incl. reinforcement and rebar installation
Insulating slab. PC flooring including SPC between tile, 65mm on PC, incl.
Providing and Laying waterproof/DPM membrane
Prefabricated Floor Slabs
Beam & hollow-core precast floor slabs
Soft flooring to levels 01 to/Roof Slabs, Stone thick
Floor Finishes
Epoxy Paint Finish
Door strips/bars
In-Situ Ceiling Finishes & Ceiling Surface Treatments
Ceiling finishes to soffit
False Ceilings and Other Prefabricated Ceiling Installations
False ceiling to data hall spaces/full offices area
SPECIAL ITEMS
Kitchen Fittings and Furnishings
Kitchen area inc. kitchen area including fittings and furnishing
Supply and fit of wardrobes including waste equipment including sink/basin
WC Fittings and Furnishings
All fittings and furnishings
Signs and Notice Boards
Information and direction signs as well as bulletin and visiting boards, M cabinets for
Other Fittings, Furnishings and Equipment
Line cost when there are specific requirement which do not fit above items
INTERNAL DOORS, WINDOWS AND CONTROL WALLS
|  |  | 2M1 |  |  |  | Internal Windows
Window to corridor / fire rated wall
Internal Doors
Internal door(s) incl.
Separation Doors, Internal Spires & Partition Walls
Separation walls incl. DL door
Furnishings & Other Fittings
Door ironmongery to single leaf doors
Door ironmongery to double leaf doors
Soft Outswing Covers
EXTERNAL WALLS / ENVELOPE
|  |  | 2X01 |  |  |  | External Windows
Windows to facades/info external
Cladding
Clad to Entrance Area
External cladding to facade generally
External Demolition to facilitate future movement of equipment
Internal Doors and Gates
Electronic card/key/pushbar door on loading bay
Other Equipment / Requirements to External Walls
ROOF
|  |  | N02 |  |  |  | Primary Roof Construction
Primary roof structure
Roof Coverings and Finishes
Gross Roof Elements
External Stairs
Canopies and Screen Walls
Canopies to loading bay
SUPERSTRUCTURE OFFICE BUILDING
SUPERSTRUCTURE OFFICE BUILDING
STRUCTURAL FRAME
|  |  | 22A |  |  |  | Structural Frame
Structural Steel: ground to first floor (including full beam)
Structural Steel elements to lift well, stairwellfre
|  |  | 22A |  |  |  | Columns
Columns
Bracing Structures
INTERNAL WALLS
|  |  | 2M1 |  |  |  | Load Bearing Internal Walls
Internal partition walls
|  |  | 22F |  |  |  | Non Load Bearing Internal Walls
Plasterboard walls, 250mm thick
Plasterboard walls, standard
Screens / Decorative Walls & Glazed Partition Walls
Cage walls incl. doors
Other Requirements to Internal Walls
INTERNAL DOORS, WINDOWS AND CONTROL WALLS
|  |  | 2M1 |  |  |  | Internal Windows
Internal Doors
Internal door(s) incl.
Separation Doors, Internal Spires & Partition Walls
Furnishings & Other Fittings
Soft Outswing Covers
EXTERNAL WALLS / ENVELOPE
Cladding, Linings & Surface Finishes to Internal Walls
Plastering and Painting to lift shaft and staircore walls
Other Equipment / Requirements to Internal Walls
IN-SITU FLOOR SLABS
|  |  | 25A |  |  |  | In-Situ Floor Slabs, Slab on Ground
Reinforced concrete slab
Prefabricated Floor Slabs
Beam & hollow-core precast floor slabs
Soft flooring to levels 01 to/Roof Slabs, Stone thick
Floor Finishes
Epoxy Paint Finish
Floor finishes to floor slab
In-Situ Ceiling Finishes & Ceiling Surface Treatments
False Ceilings and Other Prefabricated Ceiling Installations
Other Equipment / Requirements to Doors & Ceilings
SPECIAL ITEMS
Kitchen Fittings and Furnishings
Kitchen/pantry area including fittings and furnishings, as well as kitchenette including/plumbed
WC Fittings and Furnishings
All fittings and furnishings
Signs and Notice Boards
Information and direction signs as well as bulletin and visiting boards, M cabinets for
Other Fittings, Furnishings and Equipment
Line cost when there are specific requirement which do not fit above items
ROOFTOP / STRUCTURE
|  |  | 281 |  |  |  | Internal Windows
Internal Doors
Internal door(s) incl.
Furnishings and Finishes
Decoration and finishes
Other Railings, Metal-IA, & Balustrade
Other Railings including Stairs, Fences, Balustrade, etc.
Other Equipment / Requirements in Relation to Doors, Ceilings,
PASSENGER & GOODS LIFTS
PASSENGER & GOODS LIFTS
LIFTS AND CONVEYANCES
|  |  | 5M7 |  |  |  | Goods Lift (5,000 kg/3.15 m/s)
Goods Lift (5,000kg)
|  |  | 5M7 |  |  |  | Service Lift (FLRM)
Service Lift (FLRM)
MECHANICAL INSTALLATIONS
[7 empty] | MECHANICAL INSTALLATIONS |  |  |  | 186147266
MECHANICAL INSTALLATIONS GENERALLY
Commissioning: Equipment Orders, DRM, Pumps, Pressurization Unit, Degree
Lead Bank 4 Mts - 3 years(1) to include (1) series in the White Space - Temporary
Glycol Filling / drain down
Pipe Valve, Heating - Delivery
Pipe Valve, Heating - Install
HEATING INSTALLATIONS
|  |  | 336 |  |  |  | Sanitary Facilities
Sanitary installations
|  |  | 331 |  |  |  | Drainage
Drains, flat, sanitary installations
FIRE SUPPRESSION INSTALLATIONS
|  |  | 333 |  |  |  | Water installation for fire extinguishing
Fire suppression installation
COOLING SYSTEMS INSTALLATIONS
Cooling systems for building
Outdoor Chiller (Outdoor Group/Free.-A Driven/Management-Fee/Day)
Indoor/Free Cooling M-Coils/Indoor Group/Free.-1 Driven
Valves/General pipework to Glycol piping - Included in the Glycol Piping
Transport charge for Glycol piping connection to chillers
Automatic /Insect /Condensate Installation/Automatic
Inspection, Installation Certificate, Evergreen warranties not to exceed 5 years from installation
Health surveillance (condensation)
Equipment for future data halls to accommodate additional cooling
Bracket bases PSC value type/16-bar change flanges
Header Base, FGi value type/16-bar, max passage 16 connectors
Circular Pipes/Fitters Ducts, narrow passage 250mm max
Data Hall Duct Network Pressure Test
Pressure test
Process Instrumentation
Pressurization/connection with a BMS
Air Vents, automatic anti-vacuum ok
Flanged connections/Butterfly Valve(s)
Bypass and breakdown Ball Valve
3-Way Globe Valve, motorised for central control
Globe Valves
Strainers and Filters
2 Way Harness and Water Connectors
Ball Control Valve
Flexible connection items
Header Block, Steel Pipe and all accessories, including Couplings, Flanges, Bellows...
Outlet block, Steel Pipe and all accessories, including Coupling, Flanges, on
Support structure for Chilled and Cold piping, Rooftop Mounting/Routing
Trace Heating
Additional pipe/Fittings/Valves pipe and Accessories
Frost & Micro-dirt2 Chilled Water Pipe and Accessories
Frost & Micro-dirt2 Cold Water Pipe and Accessories
Chilled Water Buffer Tank / Indoor Thermal Storage (1pm Cross)
Cold Water Buffer Tank / Indoor Thermal Storage (1pm Cross)
Pumps/Expansion Valve
Pumps/Expansion Valve
Pumpset Installation
|  |  | 364 |  |  |  | Equipment for air distribution
|  |  | 364 |  |  |  | Equipment for air distribution
Supply and installation of Duct/Fittings/Valves
|  |  | 365 |  |  |  | Equipment for air treatment
Supply and Installation in Handling Unit
Items (Plant & Thermofile) - Mix, Mix
Items (Chiller) Thermofile - Mix, Mix
Valves / ERV/FP 500 - Supply
|  |  | 383 |  |  |  | Systems for purifying combustible auto
|  |  | 371 |  |  |  | Systems for purifying mechanical
Ventilation duct system manufactured and assembled installation - Oil Separator
Includes pipes, fittings, equipment as required by UK Regulation
Indirect drinking Fountains and tap sets
Clean water treatment
Process Mechanical Systems
|  |  | DKT |  |  |  | Primary Mechanical Systems
TTS - Last Detection sub: Lab Localisation
TTS - Lab Detector cell: Lab Localisation
ELECTRICAL INSTALLATIONS
[7 empty] | ELECTRICAL INSTALLATIONS |  |  |  | 231397848
ELECTRICAL INSTALLATIONS GENERALLY
Transport, orientation/site allowances
MSE, PIF, Safety supervisors (2 of A, 12 FTE overall)
Shuts, switch/electr.
Main distributor
Cable Management for Electric Power Installations
|  |  | A33 |  |  |  | Cable containment for Electric Power Installations
Cable tray(s) and accessories
Cable ladders/DLP (accessories is 15% of ladders and DLP components)
Outdoor power/ment, FCU and Server
Cable containment to Lifts from servers 1st
Cable containment/Perimeter cable tray
Separation power/IT cabling
Outdoor connector cabinets Lid
Cable Ladders, Cable Channels, Cable Bands
|  |  | A32 |  |  |  | Installation channels with audio boxes
|  |  | A71,301 |  |  |  | Grounding for Electric Power Installations
Lightning Protection
Lightning protection/YCC/Cabin
Installation for Electrical Power Outlets
Installation Channels with integrated Installations, and integrated
Branch Fabric
|  |  | MM2 |  |  |  | Safety Fixture
|  |  | A01 |  |  |  | 100 (400) Distribution
Cablework
Cabling and commissioning
|  |  | A12 |  |  |  | 100 (400) Stations and Equipment
Cabinets for HV substation
HV switchgear
HV Transformers
HV Cabinets
Cabling (Landkabel)
Cable Laying
Control and monitoring
Testing and commissioning
|  |  | A21 |  |  |  | Installations for Power Distribution
Cables, Power Cable main site transfer to generator
Busbar 400A, amp. 4P EL installation, Assembl/installation
Busbar 630A, 4 Pole 630A, delivery
Busbar 400A, amp 4P el.install(transport) not installation
Flexible connection joints
Brass nuts/risers to Cables from EPCDS (600v to the roof)
Cables, Power, Generator Power Circuit Breakers 4 pole 4P
Cables, Power, Generator Power Isolators 4 pole 4P
Cable to site, Powerboards installations
Cable to HQ, switchboards, coupling, dual supply
Cable to Lifts, Manifolds 71 x (DutCHD0) terminal filter
|  |  | A22 |  |  |  | Mains Distribution
Landed Main Switchboard: Delivering
|  |  | A22 |  |  |  | Electric Distribution for Outdoor Consumers
Breakdown of A21 DB - Installation
Breakdown of A21 3B Installation under A22380
220V Main 2x630A installation A22 38U
Cabling (right) installation then A12 DB
Cabling to Powerboard
|  |  | A26 |  |  |  | Electric Distribution to Operational Engineering Installations
440 Main 3P + Delivering
PDC racking, Power Supply, Internal racking, with plug 2 x wall/fences, 3 mains 3P
Delivering UPS pre-wiring, 30kVA - 50kVA
DRUPS board sockets and ICCL Bay for servers electricsinstall internal cabling
Cable termination and make off
AT/FL MHX supply and installation
Server Cable to Server room
Control cabinet to Server RM
|  |  | A1 |  |  |  | Lighting
Lighting incl accessories/fittings including an emergency/warning, routing/chassis
DALI Lighting System
|  |  | R63 |  |  |  | Emergency Lighting
Emergency lighting
Outdoor small power and lighting
Outdoor panel board(s)/switch cabinet
Outdoor small power and lighting
Lighting outside, Cu/PVC/s
Outdoor lighting columns
Outdoor connection cables (Flm with Card master/s)
Outdoor sockets
Outdoor receptacle
Outdoor alarm systems
Bollard lights
2.5x9 Paragon 3P hub, 3 Phase M, connection with options
Outdoor small power and lighting - High Level
Outdoor light/exterior
Outdoor light cabling
Outdoor small power and lighting - Roof
Outdoor lighting reflector/Flood with Card master/s
Outdoor lighting cable
Outdoor alarm systems
Camera systems
Camera pillars
EXTERNAL ELECTRICAL INSTALLATIONS
SPECIAL PACKAGES
[7 empty] | SPECIAL PACKAGES |  |  |  | 98506800
DTA BASIC INSTALLATIONS
|  |  | 636 |  |  |  | Security, Portal #6
DATA FIBER INSTALLATIONS
|  |  | 526 |  |  |  | Cable, Lamps and Conduits
Fiber optics/multiconductor/multi-c for servers RV rooms
|  |  | 516 |  |  |  | Conduits
Conduits, MS, RS, POS
|  |  | 512 |  |  |  | U/T/A Sockets
|  |  | 513 |  |  |  | U/T/A Distribution
BUILDING AUTOMATION
|  |  | 5X1 |  |  |  | Cabling for IA and Automation
Cabling installation
Spool Equipment
Spools and monitoring MPE panels
Control Equipment
Licenses & Equipment
|  |  | 544 |  |  |  | Fire Alarm Systems
Cabling to Fire alarm systems
Cat 6 cable to fire alarm detectors 1 zone/3 total
Painting and finishing
Access Control, Burglary and Intrusion Alarm Systems
Cabling of card readers (Door controllers) all
Cabling of card readers, supply = (+) RF Zone
Door monitoring/emergency release
Surveillance/IP camera system including connections, BMS
Procurement, Installation Certificate, Evergreen warranties not to exceed = PCS basis
Installation and cabling, conduit for inspection
Door controls/full access agency approvals for security
Testing and commissioning
Training full commissioning
CCTV AND VIDEO
CCTV internal camera surveillance and monitoring
Outdoor CCTV cabling/facade
Outdoor PIR/Camera set (CCTV camera)
Camera/video cables/junction boxes
Camera/video, mobile
Building Control and Automation
BMS/SCADA cabling
BMS monitoring and commissioning engineering
Travelling and accommodation expenses
Software, testing and commissioning
FITOUT TO TECHNICAL SPACES
FITOUT TO TECHNICAL SPACES
LOAD BEARING STRUCTURES
|  |  | 22A |  |  |  | Structural Frame
Structural Steel: ground to first floor (including full beam)
Structural Steel elements to lift well, stairwell/fire
Columns
Columns
Bracing Structures
INTERNAL WALLS
|  |  | 2M1 |  |  |  | Load Bearing Internal Walls
Precast walls to building
Non Load Bearing Internal Walls
Plasterboard walls, 250mm thick
Plasterboard walls, standard
Screens / Decorative Walls & Glazed Partition Walls
Cage walls incl. doors
Cladding, Linings & Surface Finishes to Internal Walls
Plastering and Painting to lift shaft and staircore walls
Other Requirements to Internal Walls
INTERNAL DOORS, WINDOWS AND CONTROL WALLS
|  |  | 2M1 |  |  |  | Internal Windows
Internal Doors
Internal doors, single leaf to 1.0/5 perimeter walls
Internal doors, double leaf to 1.0/5 perimeter walls
Furnishings & Other Fittings
Door ironmongery to single leaf doors
Door ironmongery to double doors
Glass Finishes
False Ceilings and Other Prefabricated Ceiling Installations
False ceiling to data hall spaces/full offices area
FITOUT FLOOR/AREA - SECTION 2
LOAD BEARING STRUCTURES
Bracing Structures
Bracing arrangement to double doors to 1.0/5 perimeter wall doors
INTERNAL WALLS
|  |  | 2M1 |  |  |  | Load Bearing Internal Walls
Precast walls to building
Non Load Bearing Internal Walls
Plasterboard walls, 250mm thick
Screens / Decorative Walls & Glazed Partition Walls
Cage walls incl. doors
Other Requirements to Internal Walls
INTERNAL DOORS, WINDOWS AND CONTROL WALLS
|  |  | 2M2 |  |  |  | Internal Doors
Internal doors, single leaf to 1.0/5 perimeter walls
Internal doors, double leaf to 1.0/5 perimeter walls
Furnishings & Other Fittings
Door ironmongery to single leaf doors
Door ironmongery to double leaf doors
Glass Finishes
False Ceilings and Other Prefabricated Ceiling Installations
False ceiling to data hall spaces/full offices area
SERVICES INSTALLATIONS
Smart/Full floor building management systems
FITOUT FLOOR/AREA - SECTION 3
LOAD BEARING STRUCTURES
Bracing Structures
Bracing arrangement to double doors to 1.0/5 perimeter wall doors
INTERNAL WALLS
|  |  | 2M1 |  |  |  | Load Bearing Internal Walls
Precast walls to building
Non Load Bearing Internal Walls
Plasterboard walls, 250mm thick
Screens / Decorative Walls & Glazed Partition Walls
Cage walls incl. doors
Other Requirements to Internal Walls
INTERNAL DOORS, WINDOWS AND CONTROL WALLS
|  |  | 2M2 |  |  |  | Internal Doors
Internal doors, single leaf to 1.0/5 perimeter walls
Internal doors, double leaf to 1.0/5 perimeter walls
Furnishings & Other Fittings
Door ironmongery to single leaf doors
Door ironmongery to double leaf doors
Glass Finishes
False Ceilings and Other Prefabricated Ceiling Installations
False ceiling to data hall spaces/full offices area
SERVICES INSTALLATIONS
Smart/Full floor building management systems
FITOUT FLOOR/AREA - SECTION 4
LOAD BEARING STRUCTURES
Bracing Structures
Bracing arrangement to double doors to 1.0/5 perimeter wall doors
INTERNAL WALLS
|  |  | 2M1 |  |  |  | Load Bearing Internal Walls
Precast walls to building
Non Load Bearing Internal Walls
Plasterboard walls, 250mm thick
Screens / Decorative Walls & Glazed Partition Walls
Cage walls incl. doors
Other Requirements to Internal Walls
INTERNAL DOORS, WINDOWS AND CONTROL WALLS
|  |  | 2M2 |  |  |  | Internal Doors
Internal doors, single leaf to 1.0/5 perimeter walls
Internal doors, double leaf to 1.0/5 perimeter walls
Furnishings & Other Fittings
Door ironmongery to single leaf doors
Door ironmongery to double leaf doors
Glass Finishes
False Ceilings and Other Prefabricated Ceiling Installations
False ceiling to data hall spaces/full offices area
SERVICES INSTALLATIONS
Smart/Full floor building management systems
FITOUT FLOOR/AREA - SECTION 5
LOAD BEARING STRUCTURES
Bracing Structures
Bracing arrangement to double doors to 1.0/5 perimeter wall doors
INTERNAL WALLS
|  |  | 2M1 |  |  |  | Load Bearing Internal Walls
Precast walls to building
Non Load Bearing Internal Walls
Plasterboard walls, 250mm thick
Screens / Decorative Walls & Glazed Partition Walls
Cage walls incl. doors
Other Requirements to Internal Walls
INTERNAL DOORS, WINDOWS AND CONTROL WALLS
|  |  | 2M2 |  |  |  | Internal Doors
Internal doors, single leaf to 1.0/5 perimeter walls
Internal doors, double leaf to 1.0/5 perimeter walls
Furnishings & Other Fittings
Door ironmongery to single leaf doors
Door ironmongery to double leaf doors
Glass Finishes
False Ceilings and Other Prefabricated Ceiling Installations
False ceiling to data hall spaces/full offices area
SERVICES INSTALLATIONS
Smart/Full floor building management systems
FITOUT FLOOR/AREA - SECTION 6
LOAD BEARING STRUCTURES
Bracing Structures
Bracing arrangement to double doors to 1.0/5 perimeter wall doors
INTERNAL WALLS
|  |  | 2M1 |  |  |  | Load Bearing Internal Walls
Precast walls to building
Non Load Bearing Internal Walls
Plasterboard walls, 250mm thick
Screens / Decorative Walls & Glazed Partition Walls
Cage walls incl. doors
Other Requirements to Internal Walls
INTERNAL DOORS, WINDOWS AND CONTROL WALLS
|  |  | 2M2 |  |  |  | Internal Doors
Internal doors, single leaf to 1.0/5 perimeter walls
Internal doors, double leaf to 1.0/5 perimeter walls
Furnishings & Other Fittings
Door ironmongery to single leaf doors
Door ironmongery to double leaf doors
Glass Finishes
False Ceilings and Other Prefabricated Ceiling Installations
False ceiling to data hall spaces/full offices area
SERVICES INSTALLATIONS
Smart/Full floor building management systems
FITOUT FLOOR/AREA - SECTION 7
LOAD BEARING STRUCTURES
Bracing Structures
Bracing arrangement to double doors to 1.0/5 perimeter wall doors
INTERNAL WALLS
|  |  | 2M1 |  |  |  | Load Bearing Internal Walls
Precast walls to building
Non Load Bearing Internal Walls
Plasterboard walls, 250mm thick
Screens / Decorative Walls & Glazed Partition Walls
Cage walls incl. doors
Other Requirements to Internal Walls
INTERNAL DOORS, WINDOWS AND CONTROL WALLS
|  |  | 2M2 |  |  |  | Internal Doors
Internal doors, single leaf to 1.0/5 perimeter walls
Internal doors, double leaf to 1.0/5 perimeter walls
Furnishings & Other Fittings
Door ironmongery to single leaf doors
Door ironmongery to double leaf doors
Glass Finishes
False Ceilings and Other Prefabricated Ceiling Installations
False ceiling to data hall spaces/full offices area
SERVICES INSTALLATIONS
Smart/Full floor building management systems
FITOUT FLOOR/AREA - SECTION 8
LOAD BEARING STRUCTURES
Bracing Structures
Bracing arrangement to double doors to 1.0/5 perimeter wall doors
INTERNAL WALLS
|  |  | 2M1 |  |  |  | Load Bearing Internal Walls
Precast walls to building
Non Load Bearing Internal Walls
Plasterboard walls, 250mm thick
Screens / Decorative Walls & Glazed Partition Walls
Cage walls incl. doors
Other Requirements to Internal Walls
INTERNAL DOORS, WINDOWS AND CONTROL WALLS
|  |  | 2M2 |  |  |  | Internal Doors
Internal doors, single leaf to 1.0/5 perimeter walls
Internal doors, double leaf to 1.0/5 perimeter walls
Furnishings & Other Fittings
Door ironmongery to single leaf doors
Door ironmongery to double leaf doors
Glass Finishes
False Ceilings and Other Prefabricated Ceiling Installations
False ceiling to data hall spaces/full offices area
SERVICES INSTALLATIONS
Smart/Full floor building management systems
POOL, GENERATORS AND CHILLERS
[7 empty] | POOL, GENERATORS AND CHILLERS |  |  |  | 474489222
POOL AND GENERATORS
Pool infrastructure (6 Transport)
POOLs - 2 EMW Transportation
POOLs, residual 630kVA one only based on PC) yet to be received from BVA
Diesel for generators
COMMISSIONING
COMMISSIONING
Commissioning year 18 - Electrical and Electrical Service Mgt
Commissioning year 18 - Mechanical
EXTERNAL WORKS AND LANDSCAPING
[7 empty] | EXTERNAL WORKS AND LANDSCAPING |  |  |  | 34860000
EXTERNAL WORKS AND LANDSCAPING
Site Ground
Network
Site Clearance and Groundworks
Bulk earthworks/general ground for excavation, backfilling, removal of
Blasting works
Mounding and minor earthworks
Landscaping / Seeding and turfing
Landscape Clearance
Drainage
Roads and Vehicle Movements
Remediation, Works and Environmental/Environment Stabilisation
Trenches and Fibre for Comms/Elec Installations
Trenching of field, drainage/Comms, Cabinets
Other Accessories and Groundworks
Other accessories and groundworks
External Walls and Fences
External wall
Steel rail x 2
Entrance Paving, Terraces and Driveways
Provisional
External Fencing
Fencing
External Gates and Direct
Direct gates
Outdoor External Reception
Outdoor signage
External Vehicle Barriers
External Culverts and Gateways
Retainers and Tanks for Stormwater installations
Retention basin - drainage
Other External Constructions
Pre laying set up on site jobs
Pipe laying on site jobs
Drainage
Re-route
Concrete PC links to utilities 200mm max
Footpath/Pedestr. to offices
Railcar
Planter
Roads
Roads, pavement and kerbing (Provisional)
Roads and Hardstanding
|  |  | T081 |  |  |  | Roads
Drain, stopcock and kerbing (Provisional)
Parking Provision
Roads (Provisional)
Pedestrian Roads (Provisional)
Signs and Signage
Utility Areas
Storm water
Drain /Drainage
Outdoor Planting
Garden areas
OPTIONAL PRICING
OPTIONAL PRICING
General contractor administration +BB 25% audit, misc and management fee
600kgs M, TDRs = 3W is, Delivering
Structural steel frame, incl. plates, HSS
Studwork, 600mm x 90s
Cladding to data halls MFR facade
Cable retical with insulation/Elec. Boards and connections
External DRUPS foundation
16 Lower & top Ceiling a Ballast raked from ceiling
Blinds, SS, welding, wiring
Emergency lighting
Mains panel boards
EDB Panel board & DB Installation
PDU to 5x 100x +500, as relocated
300 degree bus 100x + 100x incl. delivery
Power supply cabling to MDB Studios
Overhead wiring for the roof x 185mm (70 of them)
Switchboard HDCB option to incl. Source
16 Way/2P, Waterpoof SM/M residential
In/To RC/ to Floor top slab. Each POS or Gen bay. IS HEXA Extension
Misc alarm/cameras and hardware.
Drainage
Metal Power outlets
Linear power cabling and 3rd party split rectifying
External/Internal CFC/LSZH, DI, disconnection of UPS

## Variations
Change Account
CTS Nordics
CTS Ref | BVA Ref | Description of Change | Metier Estimate | Variation Account | Amount Approved | Invoice Date | Budget | Cumulative Value | Previously Certified | Total Certified | CTS Comments
VO-001 |  | Description of Change |  |  | 19860224 | d-m
VO-001 | TBC | Magnetic Filters |  |  | 1843120 |  |  | 1843125 | 0 %
VO-002 | TBC | Glycol Loop Detector Valve |  |  | 14908124 |  |  | 23160000 | 0 %
VO-003
VO-004
VO-005
VO-006
VO-007
VO-008
VO-009
VO-010
[5 empty] | 19860224 |  |  | 19885124