## Monthly report
MONTHLY REPORT |  |  |  | bulk | Bulk Infrastructure AS / bulk IKS Infra AS
PROJECT | PRO1 - Pegasus phase 2
PROJECT MANAGER
OVERALL PROJECT STATUS: BDC DC PROJECT BULDGE | BDC - under decisions in plan
Status plan defined success criteria
Report(s) | Contractual End | New Baseline | Collection | Status | Budget overview | BCWS Cumulative EA (to date) | Budget | Payment details
Infrastructure & Final Construction Design Review Complete | 02.02.2023
Wells Floors (Signal LI) og Ventil | 08.02.2023
Building Available for Client Works | 06.06.2023
Networks Rooms Clean and Available for Client works | 06.06.2023
Customer SE Mechanical Ready Include | 15.09.2023
Completed UPS Installation complete | 20.03.2024
Testing EE Emergency Early Access | 30.11.2025
White Block completed
Ventils Block completed / 1/4 signed off all
Draft CPIs issued | 01.11.2025
All block complete
Praktisk fer | 10.02.2025
IMPORTANT ISSUES/PROBLEMS

## Budget
BUDGET REPORT
Type of budget: |  | Construction project budget |  |  | Yellow background = OFFICIAL, awaiting on contract signature with CTS
Bulk company: |  | BDC Real Estate #1 |  |  | Red text = changed from last time
Periode: |  | 2023-2026
Report per: |  | 1 april 2026
Post | COST ELEMENT |  | Budget | Reestimate | Budget with allowance | Reestimate CTRL | Recommendation | payment | cumulated | Expected invoiced | Remaining
100 | COST ELEMENT
CTS safety (CRC RC 18)
CTS milestone penalties
Legal expenses
100 | D&B incl (HK sales)
110 | Incomes ERBs and EDU losses
Total building costs
200 | Infrastructure
water sewerage etc.
Kommunale tilkoblinger
300 | Outdoor works
500 | General costs - Bulk
Engineering and design entry for Bulk
600 | Legal assistance
700 | Insurance
Permits - municipality
900 | Contingency

## Current Estimate
Construction project budget
BDC Real Estate #1
2023-2026
1 april 2026
|  | Budget | Reestimate | Budget with allowance | Invoiced pr CTRL | Expected invoiced | Recommendation | payment | Remaining
COST ELEMENT
CTS safety (CRC RC 18)
CTS milestone penalties
100 | D&B incl (HK sales)
110 | Incomes ERBs and EDU losses
Total building costs
IRCs costs QC
Main contract
Commissioning support & site supervision
Leak detection and AFC install
APC
AFC mounting kit
Total
12% novation fee
IRCs costs Carter
Main contract
Commissioning support
Site supervision
Leak detection unit install
Active floor controller install & Cx
APC
AFC mounting kit
Total
12% novation fee
Net WS fit-out QC
Total WS
Total CTS with WS excl. LLI
Total CTS with WS (and backcharging) excl. LLI
LLIs
Generals
Chillers
PDCs
Total LLIs
| Total CTS |  | 1506766280
| Net backcharging TOBs and CDU losses (estimated) | 38518712
Building costs
Total CTS & QC
IRC Carter & QC
Fiber and BMS
Load bank breakers
LI battery EPODs
Fuel polisher
Pristina
Total building costs
Total building costs incl. Backcharging TOBs & CDUs
General costs
Internal hours
External hours
Engineering and design works
Legal assistance
Insurance
Permits - municipality
| Total general costs | 78500000
Finance costs
Guarantees
| Total excl. Backcharging QC and Carter | 1877435660.84
| Total incl. Backcharging TOBs & CDU losses | 1834916978.94
| Total incl. Backcharging TOBs & CDU losses + Accretion costs Carter | 1584916978.94
| Remaining fit-out costs 3 HACs QC | 78974255.13

## Code plan
Plan paa budsjett post nr. og regnskapskoder
| Costlines | PTM gjelde | Beskrivelse | Status notes | Status
| 10A | CTS D&B Contract 1MF | CTS att D&B contractors | Dryness
| 100 | Dekonstruksjon/renoveringskostnader | HVAC etc
|  | LIS fit-out | CTS as separate WS contractors 300 new
|  | Garmasjoner | PTM gjenne
Lokalsjon
|  | Elektro | Multiconsult Ver 7.3
|  | T-Rep | Not relevant covered in project 237
| R01 | Internal hours - Bulk
Mixed PM hours from 14/10/21 088

## Variations
PRO1 - Pegasus 2 - Variation tracker/budget
Stat Count | Variation Ref | VO Reference | Issued to Bulk | Status | Date | Description | Currency | Value | NOK value | Comment
|  | 1000-VO-001 |  | Issued to Bulk | None
|  | 1000-VO-002 |  | Issued to Bulk | Agreed | Change to BST heat exchanger
|  | 1000-VO-003 |  | Issued to Bulk | Agreed | Ombygging av rom
|  | 1000-1-GP-01 |  |  | Agreed | Sist Cost Estimation
|  | 1000-1-GP-013 |  | Issued to Bulk | Agreed | Change to the BF
|  | 1000-VO-004 |  | Issued to Bulk | Agreed
|  | 1000-VO-005 |  | Issued to Bulk | Agreed | Tilpasninger x 2 Pool Floor cable
|  | 1000-VO-006 |  | Issued to Bulk | Agreed | Endringer
|  | 1000-VO-007B |  | Issued to Bulk | Agreed | Revision transit Cable Route
|  | 1000-VO-008 |  | Issued to Bulk | Agreed | Housing of Fire file
|  | 1000-VO-008.1 |  | Issued to Bulk |  | Busbar Relocate - LI Testing
|  | 1000-VO-009 |  | Issued to Bulk | Agreed | Water remediation
|  | 1000-VO-010 |  | Issued to Bulk | Rejected
|  | 1000-VO-011 |  | Issued to Bulk | Agreed | Piling up
|  | 1000-VO-012 |  | Issued to Bulk | Agreed | Concrete RC addition
|  | 1000-VO-013 |  | Issued to Bulk | Agreed | Endringer generelt
|  | 1000-VO-014 |  | Issued to Bulk | Agreed | Additional Logistics Routes
|  | 1000-VO-015 |  | Issued to Bulk |  | Revision transit cable route
|  | 1000-VO-016 |  | Issued to Bulk | Agreed | Hot water of fire MV
|  | 1000-VO-017 |  | Issued to Bulk | Agreed | Full Plan Millennium P2 EL
VO Amount NOK
Contract GMP
Revised GMP

## Paid
239 Payment DCM102 Pegasus PHASE 2
CTs Nordics AS
NKI Real Estate AS
Multiconsult Asynjal AS
Schneider Electric Design AS
Schneider Electric Norge AS
F03 Interimskost budsjett/implementering
Bramble Norge AS
Schneider Electric Norge AS
R60 Regningsarbeid og andre
Bulk Data Centers N01 (Ctrl) AS
BMG utvikling + Operating Management Balances
Bramble Norge AS
Schneider Electric Norge AS
R60 Regningsarbeid og B-drift administrasjon
Bulk Data Centers N01 (Ctrl) AS
N+1 True Estate AS
Nator Prosjekt AS
Delfa LAPP
MEVALIO
IRM Energizer AS
Total & Framtidsnett
Total