## Cost Plan Cover
CTS Nordics
PRO1050 - Pegasus 2
Application for Payment
Bulk Data Centers N01 DCM102 AS
18 September 2025
Application for Payment No.14 - Mar 26

## Cumulative To Date
PRO1050 - Pegasus 2 |  |  |  | CTS Nordics | 18 September 2025
EXECUTIVE SUMMARY
Application for Payment No.14 - Mar 26
Ref | Element | GVL | Progress to Date (%) | Cumulative to Date | Previously Certified | In the Period | CTS Nordics Comments
1 | MECHANICAL INSTALLATIONS
2 | ELECTRICAL INSTALLATIONS
3 | Power Systems
4 | Cooling Systems
5 | SPECIAL PACKAGES
6 | FITOUT/DATA HALLS
PROJECT WORKS - VARIABLE PART
LLI - POOL GENERATORS & CHILLERS
(Long Lead Items)
PROJECT WORKS + LLI
PRELIMINARIES / OVERHEADS
PROJECT "MAXIMUM PRICE" (Exclusive of VAT)
AGREED CHANGE ORDERS
PROJECT "ADJUSTED CONTRACT" GMP (Exclusive of VAT)
Downpayment / Payback

## 1. Preliminaries
PRELIMINARIES | [5 empty] | CTS Nordics
Application for Payment No.14 - Mar 26
T&T Valuation
Location ID (Lvl.) | Element ID (M (+)) | Compo Compet | Type | Description | Quantity | Unit | Unit Cost | Total Cost | GMP Value | Progress to Date (%) | Cumulative Value | Previously Certified | In the Period | Progress To Date | Cumul. Value | Previous | Period
PRELIMINARIES
A | PR |  |  | Consumables charges internal
Project Attendances
Site Boundaries during construction
Protections
Fire alarms in building and barriers
Scaffolding (Provisional)
Temporary of CTS Team
Consumption charges Water
Consumption charges Electricity
Consumption charges Internet
Project insurance

## 2c. Fitout Phase 2
FITOUT TO TECHNICAL SPACES | [5 empty] | CTS Nordics
Application for Payment No.14 - Mar 26
T&T Valuation
Location ID (Lvl.) | Element ID (M (+)) | Compo Compet | Type | Description | Quantity | Unit | Unit Cost | Total Cost | GMP Value | Progress to Date (%) | Cumulative Value | Previously Certified | In the Period | Progress To Date | Cumul. Value | Previous | Period
GROUND FLOOR FITOUT HALL (S.1)
INTERNAL WALLS, DOORS, WINDOWS AND CEILING WALLS
Internal Doors
Luminaires & Other Fitworks in Internal Walls
Other Requirements in Internal Walls
INTERNAL DOORS, WINDOWS AND CEILING WALLS
Internal Doors
Luminaires & Other Fittings
STAIRWAY, FLOORS AND CEILING WALLS
Floor Finishes
False Ceilings and Other Prefabricated Ceiling Installations
PAINTING, TILING AND WALL COVERING
Painting
Luminaires & Tiles
Non-Load Bearing Internal Walls
Separator/Generator Walls & Glazed Partition Walls
Other Requirements in Internal Walls

## 3. Mechanical Phase 2
MECHANICAL INSTALLATIONS | [5 empty] | CTS Nordics
Application for Payment No.14 - Mar 26
T&T Valuation
Location ID (Lvl.) | Element ID (M (+)) | Compo Compet | Type | Description | Quantity | Unit | Unit Cost | Total Cost | GMP Value | Progress to Date (%) | Cumulative Value | Previously Certified | In the Period | Progress To Date | Cumul. Value | Previous | Period
MECHANICAL INSTALLATIONS
MECHANICAL INSTALLATIONS GENERALLY
Commissioning - Piping, Valves/Isolation Jack, Triggers, Boxes...
SANITARY INSTALLATIONS
Plumber Installation for Sanitary Installations
HEATING INSTALLATIONS
Hot water pipe installations/planning
Pipe insulation and heat tracing
HVAC AND VENTILATION
Smart Piping and Ductable ventilation
HOT WATER AND DISTRIBUTION
External Supply Piping Distribution

## 4. Electrical Phase 2
ELECTRICAL INSTALLATIONS | [5 empty] | CTS Nordics
Application for Payment No.14 - Mar 26
T&T Valuation
Location ID (Lvl.) | Element ID (M (+)) | Compo Compet | Type | Description | Quantity | Unit | Unit Cost | Total Cost | GMP Value | Progress to Date (%) | Cumulative Value | Previously Certified | In the Period | Progress To Date | Cumul. Value | Previous | Period
ELECTRICAL INSTALLATIONS
ELECTRICAL INSTALLATIONS - GENERALLY
Electrical installation items MV and Mains...
Trunking and carrier supports Lt Lt..
ELECTRIC BASIC INSTALLATIONS
Lighting
Lighting MBDE including procurement handling etc
Containment Railing
Sub Distribution
Outdoor small power and lighting - Flad
Earthing and Lightning
EMERGENCY ELECTRICAL POWER
Central Uninterruptible Cables and Automation

## 4b. Phase 2 White Space 1 Floor
ELECTRICAL INSTALLATIONS | [5 empty] | CTS Nordics
Phase 2 White Space 1 Floor
T&T Valuation
Location ID (Lvl.) | Element ID (M (+)) | Compo Compet | Type | Description | Quantity | Unit | Unit Cost | Total Cost | GMP Value | Progress to Date (%) | Cumulative Value | Previously Certified | In the Period | Progress To Date | Cumul. Value | Previous | Period

## 5. Special Phase 2
SPECIAL INSTALLATIONS | [5 empty] | CTS Nordics
Application for Payment No.14 - Mar 26
T&T Valuation
Location ID (Lvl.) | Element ID (M (+)) | Compo Compet | Type | Description | Quantity | Unit | Unit Cost | Total Cost | GMP Value | Progress to Date (%) | Cumulative Value | Previously Certified | In the Period | Progress To Date | Cumul. Value | Previous | Period
ALARM SYSTEM/DAS
Fire Alarm Systems
Configure to point of Final Design
Access Control, Security and Intrusion, Alarm Systems
CCTV/Surveillance
DATA SYSTEMS/DAS
Communications cabling install
CTS Equipment cabling, bonding

## 5c. Commissioning
COMMISSIONING | [5 empty] | CTS Nordics
Application for Payment No.14 - Mar 26
T&T Valuation
Location ID (Lvl.) | Element ID (M (+)) | Compo Compet | Type | Description | Quantity | Unit | Unit Cost | Total Cost | GMP Value | Progress to Date (%) | Cumulative Value | Previously Certified | In the Period | Progress To Date | Cumul. Value | Previous | Period
COMMISSIONING
MECHANICAL AND ELECTRICAL SERVICES
Maintenance and Electrical Services (P.Rdce)

## 6b. POC Phase 2
POOL, GENERATORS AND CHILLERS | [5 empty] | CTS Nordics
Application for Payment No.14 - Mar 26
T&T Valuation
Location ID (Lvl.) | Element ID (M (+)) | Compo Compet | Type | Description | Quantity | Unit | Unit Cost | Total Cost | GMP Value | Progress to Date (%) | Cumulative Value | Previously Certified | In the Period | Progress To Date | Cumul. Value | Previous | Period
External Cladding
Shading for services
Concrete RC work - Generators, 300mm thick
Gravity Stand Work - Chillers
Post Fittings semi
ROADS AND PARKING
Roads
Hedgehog/bush

## 7. External Phase 2
EXTERNAL WORKS | [5 empty] | CTS Nordics
Application for Payment No.14 - Mar 26
T&T Valuation
Location ID (Lvl.) | Element ID (M (+)) | Compo Compet | Type | Description | Quantity | Unit | Unit Cost | Total Cost | GMP Value | Progress to Date (%) | Cumulative Value | Previously Certified | In the Period | Progress To Date | Cumul. Value | Previous | Period
EXTERNAL CONNECTIONS
External Cladding
Shading for services
Concrete RC work
ROADS AND PARKING
Roads
Fences/Gates
Landscaping/bush

## 9. Variation Orders
CHANGE ORDERS |  |  | CTS Nordics
Application for Payment No.14 - Mar 26
VO No. | Description of Change | VO Status | Approved | Cumulative | CTS Comments
VO-001 | Screens (MVDB) Floor Section for MIST Centre(s)
VO-002 | Underground Foundation Site Section for Buffe Tank
VO-003
VO-005 | Variation (MVOB) - Fire Bollard
VO-006 | Design for the Remaining BU Cooling Water Installation
VO-007 | Extension of Road G1 to Pegasus Phase
VO-008 | (R) & B Commission Testing - Rejected
VO-009
VO-010 | Perimeter Testing and site work for corridor of building
VO-011 | Additional Roof/Lift exposed Testing Rooms
VO-012 | Ice Store changes in cooling plant
VO-013 | Additional Pipework for Fire Suppression
VO-014 | Cable Tray connection to the M&S room
VO-015 | Addition of Cable tray in Field floor and connections per QC Rooms
VO-016 | Change to chiller piping Pegasus system
VO-017 | Variation to BMS R Bulk L s Office
VO-018 | Raised to Dota A links
VO-019 | Process Piping Equipment and UL Fasting
VO-020 | 250mm Pipe - changes to GIS Fiber M01
VO-021 | Additional Roof Lift exposed Testing Rooms
VO-022 | CWA testing of Feedwater CRLL50
VO-023 | Estimated Roof air handling Control of soft walls/Installations
VO-024 | Additional Floor conditioned
VO-025 | Conversion of data cables